## HT
CHAMUNDESWARI ELECTRICITY SUPPLY CORPORATION LIMITED
ESTIMATE FOR CREATING INFRASTRUCTURE TO REGISTERED/ REGULARISED IP SETS UNDER TOTAL TURNKEY BASIS
SECTION OFFICER NAME :MAHADEV.D |  | EST NO/DATE : TM-330 05/02/2022
SECTION : HOSUR |  | VILLAGE NAME : BENAGANAHALLI
SUBDIVISION : K.R.NAGARA |  | FEEDER NAME : KOTHAVALLI IP
EXISTING DTC CODE :1512CL |  | EXISTING TRANSFORMER CAPACITY: 25KVA
NO OF IP SETS ON EXISTING TRANS:06 AUTH:06 UNAUTH:00 |  | CONNECTED LOAD OF THE TRANSFORMER: 30HP
NO OF IPS/LOAD TRANSFERED TO PROPOSED 25 KVA TRANSFORMER: |  | 03 /15HP
DWA No & Date.:CESC/GM(P)/DGM(P)/AGM(P-1)/2021-22/14111-13 Dated: 26.11.2021
Schedule -1: Extension of HT line PART-A
Sl.No | Materials | Unit | Qty | Rates as per CESC SR 2022-23 |  |  |  | DWA Rates 13% over the Sept-21 IEEMA updated price CSR 2018-19
|  |  |  | Material |  | Labour
|  |  |  | Rate | Amount | Rate | Amount | Rate | Amount | Rate | Amount
1 | 9 mtr long RCC pole 145KG WL | Nos | 1 | 7153 | 7153 | 1341 | 1341 | 8416 | 8416 | 2068 | 2068 | 0.15007
2 | 9 mtr long PSC pole 200KG WL | Nos | 0 | 4276 | 0 | 1341 | 0 | 5031 | 0 | 2068 | 0 | 0.15007
3 | Rabbit ACSR conductor | Km | 0.12 | 61515 | 7381.8 | 3299 | 395.88 | 59913 | 7189.56 | 5089 | 610.68 | -0.026739
4 | 11kV, 5kN composite/Polymeric pin insulator including DTC Structure | Nos | 0 | 221 | 0 | 0 | 0 | 228 | 0 | 0 | 0 | 0.030702
5 | 11kV 45kN polymeric Dead end insulators including DTC structure | Nos | 6 | 202 | 1212 | 0 | 0 | 208 | 1248 | 0 | 0 | 0.028846
6 | 11kV Horizontal cross arms GI with clamp, HTST, bolts & nuts of required size and washers etc for RCC pole | Set | 2 | 668 | 1336 | 122 | 244 | 711 | 1422 | 188 | 376 | 0.060478
7 | 11kV Horizontal cross arms GI with clamp, HTST, bolts & nuts of required size and washers etc for PSC pole | Set | 2 | 664 | 1328 | 122 | 244 | 707 | 1414 | 188 | 376 | 0.06082
8 | D.P.Structure using 9 mtrs RCC poles including cost of poles | Set | 0 | 21369 | 0 | 4114 | 0 | 24731 | 0 | 6348 | 0 | 0.13594
9 | Guy set complete with No.15 strain insulator and concreting materials | Set | 1 | 1209 | 1209 | 448 | 448 | 1547 | 1547 | 692 | 692 | 0.21849
10 | Guy Concreting with Boulders, Mud and Sand | Nos | 1 | 0 | 0 | 200 | 200 | 0 | 0 | 308 | 308 | #DIV/0!
11 | PG clamps for Rabbit conductor Only 3 for HT | Nos | 6 | 116 | 696 | 0 | 0 | 92 | 552 | 0 | 0 | -0.26087
12 | Spiral earth electrode | Nos | 1 | 248 | 248 | 70 | 70 | 215 | 215 | 107 | 107 | -0.15349
Total Cost |  |  |  |  | 20563.8 |  | 2942.88 |  | 22003.56 |  | 4537.68
2 | Escom Establishement Cost @ 20 % on Labour Charges |  |  |  | 588.576 |  |  |  | 26541.24
3 | Goods and Service Tax (GST)18 % on Labour Charges |  |  |  | 529.7184
4 | EPF and ESI @ 17.75% on labour Charges |  |  |  | 522.3612
5 | Transportation cost stores to Site at 2% on Material Cost |  |  |  | 411.276
6 | Insurance cost against theft and accident at 1% on Material Cost |  |  |  | 205.638
7 | Elecrical Inspectorate Charges |  |  |  | 1000
8 | Watch and ward cost at 1%on Material Cost |  |  |  | 205.638
9 | Contigencies @ 2% above total Material and Labour Cost |  |  |  | 470.1336
| Total cost |  |  |  | 27440.0212
Total Cost |  | 26541.24
| Junior Engineer(Ele), O&M Section, CESC, HOSUR | Assistant Executive Engineer(Ele) O&M Sub-Division, CESC,KR Nagara

## DTC
CHAMUNDESWARI ELECTRICITY SUPPLY CORPORATION LIMITED
ESTIMATE FOR CREATING INFRASTRUCTURE TO REGULARISED IP SETS UNDER PARTIAL TURNKEY BASIS
SECTION OFFICER NAME :MAHADEV.D |  | EST NO/DATE : TM-330 05/02/2022
SECTION : HOSUR |  | VILLAGE NAME : BENAGANAHALLI
SUBDIVISION : K.R.NAGARA |  | FEEDER NAME : KOTHAVALLI IP
EXISTING DTC CODE :1512CL |  | EXISTING TRANSFORMER CAPACITY: 25KVA
NO OF IP SETS ON EXISTING TRANS:06 AUTH:06 UNAUTH:00 |  | CONNECTED LOAD OF THE TRANSFORMER: 30HP
NO OF IPS/LOAD TRANSFERED TO PROPOSED 25 KVA TRANSFORMER: |  | 03 /15HP
DWA.No & Date.:CESC/GM(P)/DGM(P)/AGM(P-1)/2019-20/DWA:396-397/1531-34 dated: 30.04.2020
Schedule -2 : Providing 1X25 KVA DTC PART-B
Sl.No | Materials | Unit | Qty | Rates as per CESC SR 2022-23 |  |  |  | DWA Rates 13% over the Sept-21 IEEMA updated price CSR 2018-19
|  |  |  | Material |  | Labour
|  |  |  | Rate | Amount | Rate | Amount | Rate | Amount | Rate | Amount
PART_A Agency Portion
1 | 9 mtr RCC DP transformer structure (using 9 mtr RCC poles) | Nos | 1 | 32553 | 32553 | 5205 | 5205 | 38304 | 38304 | 8031 | 8031 | 35.19% | 15.01% | 3724 | 5120.5
2 | 11kV/433V, 25 KVA , 3 phase, 50 Cys Distribution transformer BEE- 4 star rated with oil | Nos | 1 | 87950 | 87950 | 863 | 863 | 100039 | 100039 | 1331 | 1331 | 35.16% | 12.08% |  | 33183.5
3 | Guy set complete with No.15 strain insulator and concreting materials | Set | 2 | 1209 | 2418 | 448 | 896 | 1547 | 3094 | 692 | 1384 | 35.26% | 21.85% |  | #REF!
4 | Guy Concreting with Boulders, Mud and Sand | Set | 2 | 0 | 0 | 200 | 400 | 0 | 0 | 308 | 616 | 35.06% | #DIV/0!
5 | Earthing materials pipe type for grounding as per Drawing | Set/3Nos | 1 | 5199 | 5199 | 2205 | 2205 | 5852 | 5852 | 3358 | 3358 | 34.34% | 11.16%
6 | Caution/Danger board as per approved drawing | Nos | 1 | 146 | 146 | 61 | 61 | 171 | 171 | 94 | 94 | 35.11% | 14.62%
7 | Anti - Climbing Device (12mtrs / 1 kg G.I. Barbed Wire) Lumpsum | Kgs | 2 | 93 | 186 | 32 | 64 | 98 | 196 | 49 | 98 | 34.69% | 5.102%
8 | GI wire 8 SWG | Kgs | 5 | 77.85 | 389.25 | 0 | 0 | 82 | 410 | 0 | 0 | #DIV/0! | 5.061%
9 | Guy wire 7/10 SWG | Kgs | 10 | 80.12 | 801.2 | 0 | 0 | 84 | 840 | 0 | 0 | #DIV/0! | 4.619%
10 | a) LT Protection kit | Nos | 1 | 1915 | 1915 | 260 | 260 | 2020 | 2020 | 401 | 401 | 35.16% | 5.198%
11 | b) LT wiring (From DTCto LT through metering Box & LT protection Kit) | Nos | 1 |  | 0 |  |  | 0 | 0 | 0 |  | #DIV/0! | #DIV/0!
| i) A1 Lead wire-50 sqmm | Mt | 25 | 79.46 | 1986.5 | 719 | 719 | 78 | 1950 | 1109 | 1109 | 35.17% | -1.872%
| ii) Cu Lugs-50 sqmm | Nos | 8 | 60 | 480 |  |  | 67 | 536 |  | 0 | #DIV/0! | 10.45%
| iii) PG clamps - Rabbit to 50 sqmm | Nos | 4 | 116 | 464 |  |  | 111 | 444 |  | 0 | #DIV/0! | -4.505%
| iv) Spacers for DTC wiring | Nos | 8 | 41 | 328 |  |  | 48 | 384 |  | 0 | #DIV/0! | 14.58%
| v) Fish plate with necessary clamps, bolts & nuts etc.,complete (Galvanised) | Nos | 2 | 229 | 458 |  |  | 229 | 458 |  | 0 | #DIV/0! | 0%
12 | 11 kV lightning Arrester , Metal oxide, 9 kV, 5 kA | Set/3Nos | 1 | 1736 | 1736 | 90 | 90 | 1617 | 1617 | 138 | 138 | 34.78% | -7.359%
13 | 11kV 200 Amps Single Break GOS | Set | 1 | 9125 | 9125 | 805 | 805 | 10186 | 10186 | 1241 | 1241 | 35.13% | 10.42%
14 | HG Fuse, 11 kV Solid Core Type | Set/3Nos | 1 | 1032 | 1032 | 178 | 178 | 1089 | 1089 | 274 | 274 | 35.04% | 5.234%
[5 empty] | 147166.95 |  | 11746 |  | 167590 |  | 18075
2 | Escom Establishement Cost @ 20 % on Labour Charges |  |  |  | 2349.2 |  |  |  |  | 185665
3 | Goods and Service Tax (GST)18 % on Labour Charges |  |  |  | 2114.28
4 | EPF and ESI @ 17.75% on labour Charges |  |  |  | 2084.915
5 | Transportation cost stores to Site at 2% on Material Cost |  |  |  | 2943.339
6 | Insurance cost against theft and accident at 1% on Material Cost |  |  |  | 1471.6695
7 | Electrical Inspectorate charges |  |  |  | 1600
8 | Watch and ward cost at 1% on Material Cost |  |  |  | 1471.6695
9 | Contigencies @ 2% above total |  |  |  | 3178.259
| Total cost |  |  |  | 176126.282
Junior Engineer(Ele), O&M Section, CESC, HOSUR |  | Assistant Executive Engineer(Ele) O&M Sub-Division, CESC,KR Nagara

## LT
CHAMUNDESWARI ELECTRICITY SUPPLY CORPORATION LIMITED
ESTIMATE FOR CREATING INFRASTRUCTURE TO REGULARISED IP SETS UNDER PARTIAL TURNKEY BASIS
SECTION OFFICER NAME :MAHADEV.D |  | EST NO/DATE : TM-330 05/02/2022
SECTION : HOSUR |  | VILLAGE NAME : BENAGANAHALLI
SUBDIVISION : K.R.NAGARA |  | FEEDER NAME : KOTHAVALLI IP
EXISTING DTC CODE :1512CL |  | EXISTING TRANSFORMER CAPACITY: 25KVA
NO OF IP SETS ON EXISTING TRANS:06 AUTH:06 UNAUTH:00 |  | CONNECTED LOAD OF THE TRANSFORMER: 30HP
NO OF IPS/LOAD TRANSFERED TO PROPOSED 25 KVA TRANSFORMER: |  | 03 /15HP
DWA No & Date.:CESC/GM(P)/DGM(P)/AGM(P-1)/2021-22/14111-13 Dated: 26.11.2021
Schedule -3: Extension of LT line PART-C
Sl.No | Materials | Unit | Qty | Rates as per CESC SR 2022-23 |  |  |  | DWA Rates 13% over the Sept-21 IEEMA updated price CSR 2018-19
|  |  |  | Material |  | Labour
|  |  |  | Rate | Amount | Rate | Amount | Rate | Amount | Rate | Amount
1 | 8 mtrs long RCC poles 115kg WL | Nos | 0 | 5306 | 0 | 1072 | 0 | 6243 | 0 | 1653 | 0
2 | 8 mtrs long PSC poles 200kg WL | Nos | 0 | 3578 | 0 | 1072 | 0 | 4210 | 0 | 1653 | 0
3 | Weasel ACSR Conductor | Km | 0 | 37018 | 0 | 2420 | 0 | 35308 | 0 | 3733 | 0
5 | Releasing and Refixing of 4 Pin cross arms with pole clamp, B&N of required size and washers etc for PSC pole | Set | 3 | 435 | 0 | 122 | 0 | 1305 | 0 | 414 | 695.4
6 | 4 Pin cross arms with pole clamp, B&N of required size and washers etc for RCC pole | Set | 1 | 439 | 439 | 122 | 122 | 389 | 389 | 188 | 188
7 | 4 Pin cross arms with pole clamp, B&N of required size and washers etc for PSC pole | Set | 0 | 435 | 0 | 122 | 0 | 384 | 0 | 188 | 0
8 | Pin Insulators 1.1KV class with G.I.Pins, nuts & Washers | Nos | 0 | 65 | 0 | 0 | 0 | 68 | 0 | 0 | 0
9 | No.8 Strain Insulators | Nos | 8 | 25 | 200 |  | 0 | 25 | 200 | 0 | 0
10 | Guy set complete with No.15 strain insulator and concreting materials | Set | 1 | 1209 | 1209 | 448 | 448 | 1397 | 1397 | 692 | 692
11 | Guy Concreting with Boulders, Mud and Sand | Nos | 1 | 0 | 0 | 200 | 200 | 0 | 0 | 308 | 308
Total Cost |  |  |  |  | 1848 |  | 770 |  | 1986 |  | 1883.4
1 | Locality Allownace @ 30% on Labour Charges |  |  |  | 0 |  |  |  |  | 3869.4
2 | Escom Establishement Cost @ 20 % on Labour Charges |  |  |  | 154
3 | Goods and Service Tax (GST)18 % on Labour Charges |  |  |  | 138.6
4 | EPF and ESI @ 17.75% on labour Charges |  |  |  | 136.675
5 | Transportation cost stores to Site at 2% on Material Cost |  |  |  | 36.96
6 | Insurance cost against theft and accident at 1% on Material Cost |  |  |  | 18.48
7 | Elecrical insporate charges |  |  |  | 500
8 | Watch and ward cost at 1% on Material Cost |  |  |  | 18.48
9 | Contigencies @ 2% above total |  |  |  | 52.36
| Total cost |  |  |  | 3673.555
| Junior Engineer(Ele), O&M Section, CESC, HOSUR | Assistant Executive Engineer(Ele) O&M Sub-Division, CESC,KR Nagara

## DEC
CHAMUNDESWARI ELECTRICITY SUPPLY CORPORATION LIMITED
ESTIMATE FOR CREATING INFRASTRUCTURE TO REGULARISED IP SETS UNDER TOTAL TURNKEY BASIS
SECTION OFFICER NAME :MAHADEV.D |  | EST NO/DATE : TM-330 05/02/2022
SECTION : HOSUR |  | VILLAGE NAME : BENAGANAHALLI
SUBDIVISION : K.R.NAGARA |  | FEEDER NAME : KOTHAVALLI IP
EXISTING DTC CODE :1512CL |  | EXISTING TRANSFORMER CAPACITY: 25KVA
NO OF IP SETS ON EXISTING TRANS:06 AUTH:06 UNAUTH:00 |  | CONNECTED LOAD OF THE TRANSFORMER: 30HP
NO OF IPS/LOAD TRANSFERED TO PROPOSED 25 KVA TRANSFORMER: |  | 03 /15HP
DWA No & Date.:CESC/GM(P)/DGM(P)/AGM(P-1)/2021-22/14111-13 Dated: 26.11.2021
Part D, Decommissioning of Assets
Sl No | Particulars | Unit | Qty | Rates as per CESC SR 2022-23 |  | DWA Rates 13% over the Sept-21 IEEMA updated price CSR 2018-19
1 | Releasing of 9 Mtr RCC Poles, 8Mtr | Nos | 0 | 1206.9 | 0 | 2068 | 0
2 | Releasing of 8 Mtr PSC Poles, 8Mtr | Nos | 0 | 965 | 0 | 1653 | 0
3 | Releasing of 2ACSR Conductor | Kms | 0 | 2969.1 | 0 | 3733 | 0
4 | Releasing of 4ACSR Conductor | Kms | 0.12 | 2178 | 235.224 | 3733 | 403.164 | 1206.9
5 | Releasing of Horizontal Cross arms | Nos | 0 | 109.8 | 0 | 188 | 0
6 | Releasing of 4 pin Cross arms | Nos | 0 | 109.8 | 0 | 188 | 0
| Total |  |  |  | 235.224 |  | 403.164
1 | Locality Allowance @ 30% on LC |  |  |  | 70.5672 |  |  |  | 964.8
2 | Total Labour Cost |  |  |  | 305.7912
3 | GST Service Tax @ 18% on Total Labour Cost |  |  |  | 55.0424
4 | Escom Establishement Cost @ 20 % on Labour Charges |  |  |  | 54.2779
5 | Contribution towards EPF & ESI Charges @ 17.75% on Total Labour Charge |  |  |  | 54.2779
6 | Contingencies @ 2% on Total Material & Labour Cost |  |  |  | 6.1158
| Total Cost |  |  |  | 475.5053
Paarticulars of Assets to be released Materials and returnable to store.
1 | Releasing of 9 Mtr RCC Poles, 8Mtr | Nos | 0 | Skeleton
2 | Releasing of 8 Mtr PSC Poles, 8Mtr | Nos | 0 | Not Return to store
3 | Releasing of 2ACSR Conductor | Kms | 0 | 90% Returnable-Scrap-0.0KMx114Kg=0KG
4 | Releasing of 4ACSR Conductor | Kms | 0.12 | 90% Returnable-Scrap- 0.12KMx76Kg= 9KG
5 | Releasing of Horizontal Cross arms | Nos | 0
6 | Releasing of 4 pin Cross arms | Nos | 0
| Date of commissioning | More than 20 Years
| Date of Release | After Sanctioning the Estimate
Particulars to be furnished by Account staff.
1 | Original Cost :
2 | Depreciation Earned :
3 | Returndown Value :
Junior Engineer(Ele), O&M Section, CESC, HOSUR |  | Assistant Executive Engineer(Ele) O&M Sub-Division, CESC,KR Nagara

## Report
CHAMUNDESWARI ELECTRICITY SUPPLY CORPORATION LIMITED
ESTIMATE FOR CREATING INFRASTRUCTURE TO REGISTERED/ REGULARISED IP SETS UNDER TOTAL TURNKEY BASIS
SECTION OFFICER NAME :MAHADEV.D |  | EST NO/DATE : TM-330 05/02/2022
SECTION : HOSUR |  | VILLAGE NAME : BENAGANAHALLI
SUBDIVISION : K.R.NAGARA |  | FEEDER NAME : KOTHAVALLI IP
EXISTING DTC CODE :1512CL |  | EXISTING TRANSFORMER CAPACITY: 25KVA
NO OF IP SETS ON EXISTING TRANS:06 AUTH:06 UNAUTH:00 |  | CONNECTED LOAD OF THE TRANSFORMER: 30HP
NO OF IPS/LOAD TRANSFERED TO PROPOSED 25 KVA TRANSFORMER: |  | 03 /15HP
DWA No & Date.:CESC/GM(P)/DGM(P)/AGM(P-1)/2021-22/14111-13 Dated: 26.11.2021
Abstract: | Estimate Cost | Award Amount
Sechedule 1:Extention of HT line | 27440.0212 | 26541.24
Sechedule 2:Providing 1X25 KVA DTC | 176126.282 | 185665
Sechedule 3:Extension of LT line | 3673.555 | 3869.4
Sechedule 4: Decommissioning | 475.5053 | 403.164
Total Estimate Cost | 207715.3635 | 216478.804
zsÀÈrüÃPÀgÀt
ಹೊಸೂರು ±ÁSÉ ªÁå¦ÛAiÀÄ°è£À ಬೆನಗನಹಳ್ಳಿ UÁæªÀÄzÀ ªÁå¦ÛAiÀÄ°è£À, 1 *25 PÉ.«.J ¸ÁªÀÄxÀåðzÀ ¥ÀjªÀvÀðPÀzÀ (r.n.J¯ï.JA.J¸ï:1512CL) ªÉÄÃ¯É C¢PÀÈvÀªÁV ºÉÃgÀ¯ÁVzÀÝ ¤ÃgÁªÀj ¥ÀA¥À¸ÉmïUÀ¼À «zÀÄåvï ºÉÆgÉAiÀÄ£ÀÄß 01 ¸ÀASÉåAiÀÄ 25PÉ.«.J ¥ÀjªÀvÀðPÀ ªÀÄvÀÄÛ ªÀiÁUÀðUÀ¼À£ÀÄß ¤«Äð¸ÀÄªÀ ªÀÄÆ®PÀ C¢üPÀÈvÀªÀV ¤ÃgÁªÀj ¥ÀA¥ï-¸ÉmïUÀ¼À «zÀÄåvï ºÉÆgÉAiÀÄ£ÀÄß ¨sÉÃ¥Àðr¸À®Ä F CAzÁdÄ ¥ÀnÖAiÀÄ£ÀÄß vÀAiÀiÁj¸À¯ÁVgÀÄvÀÛzÉ
207715.3635 | gÀÆ UÀ½UÉ CAzÁdÄ ¥ÀnÖAiÀÄ£ÀÄß ¹zÀÝ¥Àr¸À¯ÁVzÉ.
ºÁ° EgÀÄªÀ 25 PÉ«K ¥ÀjªÀvÀðPÀzÀ ªÉÄÃ¯ 6 ¸ÀASÉåÉ ¤ÃgÁªÀj ¥ÀA¥ï-¸ÉmïUÀ¼À£ÀÄß C¢üPÀÈvÀªÁV ºÉÃgÀ¯ÁVzÀÝ ¤ÃgÁªÀj ¥ÀA¥ï-¸Émï£À UÁæºÀPÀgÀÄ vÀªÀÄä ¥ÀA¥ï-¸ÉmïUÀ¼À£ÀÄß ¸ÀPÀæ«ÄÃPÀj¹PÉÆ¼Àî®Ä ¤UÀ¢üvÀ ªÉÆvÀÛªÀ£ÀÄß ¤UÀªÀÄPÉÌ ¥ÁªÀw¹gÀÄvÁÛgÉ ¸ÀzÀj ªÀiÁ»wAiÀÄ£ÀÄß ®UÀwÛ¸À¯ÁVzÉ.
GzÉÝÃ²vÀ 25PÉ.«.J ¥ÀjªÀvÀðPÀªÀ£ÀÄß ºÉZÀÄÑªÀjAiÀiÁV C¼ÀªÀr¸ÀÄªÀÅzÀjAzÀ UÁæºÀPÀjUÉ GvÀÛªÀÄ UÀÄtªÀÄlÖzÀ «zÀÄåvï ¸ÀgÀ§gÁdÄ ¤ÃqÀ§ºÀÄzÁVzÀÄÝ, ¥ÀÄ£ÀgÁªÀwðvÀ ¥ÀjªÀvÀðPÀ «¥sÀ®vÉUÀ¼À£ÀÄß vÀqÉAiÀÄ§ºÀÄzÀÄ ºÁUÀÄ J¯ï.n ªÉÇÃ¯ÉÖÃeï gÉUÀÄå¯ÉÃµÀ£ï PÁ¥ÁqÀ§ºÀÄzÀÄ.
PÉ.K.Dgï.¹ ¤AiÀÄªÀÄzÀAvÉ ¥ÀæwÃ L.¦ ¸ÁÜªÀgÀUÀ¼À Dgï.Dgï ¸ÀASÉå AiÀÄ£ÀÄß ¥ÉÊAmï ªÀiÁqÀ¯ÁVzÉ. CµÀÆÖ L.¦ ¸ÁÜªÀgÀUÀ¼À£ÀÄß Enumeration ªÀiÁqÀ¯ÁV www.cescip.com £À°è £ÀªÀÄÆ¢¸À¯ÁVgÀÄvÀÛzÉ.
ºÁ° EgÀÄªÀ ¥ÀjªÀvÀðPÀzÀ ªÉÄÃ°£À ºÉÆgÉ: | (ªÀiÁ»w ®UÀwÛ¸À¯ÁVzÉ)
2021 £ÉÃ ¸Á°£À°è «¥sÀ®vÉ ¸ÀASÉå/¢£ÁAPÀ
GzÉÝÃ²vÀ ¥ÀjªÀvÀðPÀPÉÌ 11 PÉ« «zÀÄåvï ªÀiÁUÀð: | ಕೊತ್ವಲ್ಲಿ | «zÀÄåvï ªÀiÁUÀðzÀ ºÁ° ¸ÀA¥ÀQðvÀ ¨sÁgÀ
66/11PÉ.« «zÀÄåvï «vÀgÀuÁ PÉÃAzÀæ: | ಕಿತ್ತೂರ್ | «zÀÄåvï ªÀiÁUÀðzÀ ºÁ° ¸ÀA¥ÀQðvÀ ¨sÁgÀ
zsÀÈrüÃPÀgÀt ¸ÀÀzÀj CAzÁdÄ ¥ÀnÖAiÀÄ£ÀÄß RÄzÁÝV ¸ÀÜ¼À ¥Àj²Ã°¹ CvÀåAvÀ PÀrªÉÄ ªÉZÀÑzÀ°è vÁAiÀiÁj¸À¯ÁVzÀÄÝ, CªÀ±ÀåªÁzÀAvÀºÀ ¸ÁªÀÄVæUÀ¼ÀÄ ªÀÄvÀÄÛ PÀÆ° PÉ®¸ÀUÀ¼À£ÀÄß ¸ÀA¥ÀÆtð ¸ÉÃ¥Àðr¹ DWA ¸ÀASÉå CESC/GM(P)/DGM(P)/AGM(P-1)/2021-22/14111-13 Dated: 26.11.2021 gÀ£ÀéAiÀÄ vÀAiÀiÁj¸À¯ÁVgÀÄvÀÛzÉ.
Junior Engineer(Ele), O&M Section, CESC, HOSUR
¸ÀÀzÀj CAzÁdÄ ¥ÀnÖAiÀÄÄ ¤UÀªÀÄzÀ J¸ï.Dgï 2018-19 ºÁUÀÆ M/s ………………………………………………………………...……...s gÀªÀjUÉ ¤qÀ¯ÁVgÀÄªÀ DWA ªÉÆvÀÛPÉÌ ¸ÀA¥ÀÆtð vÁ¼É ºÉÆAzÀÄwÛgÀÄvÀÛzÉ
Asst Engineer (Tech), O&M Subdivision,CESC, |  | Assistant Executive Engineer(Ele) O&M Sub-Division, CESC,KR Nagara

## WO
ಚಾಮುಂಡೇಶ್ವರಿ ವಿದ್ಯುತ್ ಸರಬರಾಜು ನಿಗಮ ನಿಯಮಿತ
(ಕರ್ನಾಟಕ ಸರ್ಕಾರದ ಸ್ವಾಮ್ಯಕ್ಕೆ ಒಳಪಟ್ಟಿದೆ)
Chamundeshwari Electricity Supply Corporation Ltd.
(Wholly owned by Government of Karnataka )
PÁAiÀÄð¤ªÁðºÀPÀ EAf¤AiÀÄgï gÀªÀgÀ PÀZÉÃj |  | Office of the Executive Engineer (Ele)
PÁAiÀÄð ªÀÄvÀÄÛ ¥Á®£Á «¨ÁUÀ ZÁ.«.¸À.¤.¤ PÀÈµÀÚgÁd£ÀUÀgÀ |  | O & M Division, CESC, Krishnaraja Nagar
PÁAiÀÄðzÉÃ±À/ Work Order
CAzÁdÄ¥ÀnÖ ¸ÀASÉå | TM-116 | ¢£ÁAPÀ : | 11.01.2022
CAzÁdÄ¥ÀnÖAiÀÄ «ªÀgÀ: | Estimate for Creating infrastructure for regularised IP Sets on Existing DTC Code 1641DF by providing Additional DTC to RR Nos SCHKIP-50228, KRHIP-55710, KRHIP-60470 & KRHIP-53112 at Nadappanahalli Village Survey No 33 Hosuru Section
¯ÉPÀÌ ²Ã¶ðPÉ : | 14-3207
PÁAiÀÄðzÉÃ±À ¸ÀASÉå ದಿನಾಂಕ: 22.10.2018 | KD-2201 | ¢£ÁAPÀ : | 21.01.2022
CAzÁdÄ¥ÀnÖ ªÉÆvÀÛ gÀÆ | 207239.8582 | CªÁqïð ªÉÆvÀÛ: | 216478.804
CAzÁdÄ¥ÀnÖ ªÉÆvÀÛ | (CPÀëgÀUÀ¼À°è):JgÀqÀÄ ®PÀëzÀ DgÀÄ ¸Á«gÀzÀ K¼ÀÄ£ÀÆgÀ E¥ÀàvÀÛ JAlÄ gÀÆ¥Á¬ÄUÀ¼ÀÄ ªÀiÁvÀ.æ
¯ÉPÀÌ ²Ã¶ðPÉ : | 77-5507
PÁAiÀÄðzÉÃ±À ¸ÀASÉå ದಿನಾಂಕ: 22.10.2018 | DD-2201 | ¢£ÁAPÀ : | 21.01.2022
CAzÁdÄ¥ÀnÖ ªÉÆvÀÛ gÀÆ | 475.5053
CAzÁdÄ¥ÀnÖ ªÉÆvÀÛ | K¼ÀÄ ¸Á«gÀzÀ MA¨ÉÊ£ÀÆgÀ DgÀªÀvÀÛ JgÀqÀÄ gÀÆ¥Á¬ÄUÀ¼ÀÄ ªÀiÁvÀæ
¯ÉPÀÌ ²Ã¶ðPÉ : | 55-1057
PÁAiÀÄðzÉÃ±À ¸ÀASÉå ದಿನಾಂಕ: 22.10.2018 | KA-DEC-5451 | ¢£ÁAPÀ : | 07.11.2018
CAzÁdÄ¥ÀnÖ ªÉÆvÀÛ gÀÆ | 475.5053
CAzÁdÄ¥ÀnÖ ªÉÆvÀÛ | (CPÀëgÀUÀ¼À°è): LzÀÄ ¸Á«gÀzÀ DgÀÄ £ÀÆgÀ J¥ÀàvÀÛªÀÄÆgÀÄ gÀÆ¥Á¬ÄUÀ¼ÀÄ
µÀgÁ
¸ÀzÀj PÁªÀiÁUÁjAiÀÄ£ÀÄß ¥ÀÆtð UÀÄwÛUÉ DzsÁgÀzÀ°è FP PÉ¼ÀPÀAqÀ DWA C£ÀéAiÀÄ AiÀÄr CªÁqïð ¤ÃqÀ¯ÁVgÀÄvÀÛzÉ
DWA No & Date.:CESC/GM(P)/DGM(P)/AGM(P-1)/2021-22/14117-19 Dated: 26.11.2021
¸ÀzÀj PÁAiÀÄðzÉÃ±ÀzÀr GUÁæt¢AzÀ AiÀiÁªÀÅzÉ ¸ÁªÀiÁVæUÀ¼À£ÀÄß ¥ÀqÉzÀÄPÉÆ¼ÀÄîªÀAw®è. PÁªÀÄUÁjAiÀÄ°è PÀ¼ÀazÀ ¸ÁªÀiÁVæUÀ¼À£ÀÄß GUÁætPÉÌ »A¢gÀÄV¸À¢zÀÝ°è, ¸ÁªÀiÁVæUÉ ZÁ°ÛAiÀÄ°ègÀÄªÀ zÀgÀ/ zÀgÀzÀ£ÀéAiÀÄ vÀUÀÄ®ÄªÀ ªÉÆvÀÛPÉÌ MlÄÖ ©°è¤AzÀ PÀrvÀUÉÆ½¸À¯ÁUÀÄªÀÅzÀÄ.
F CªÁqïð ªÉÆvÀÛ:-…………………… | 216478.804 | 2021-22 £ÉÃ ¸Á°£À CªÁqïð ¤ÃrgÀÄªÀ MlÄÖ ªÉÆvÀÛ:- | 216478.804 | 0
zÀÈrüÃPÀgÀt:
F CAzÁdÄ ¥ÀnÖAiÀÄ ªÉÆvÀÛ:-…………………… | 207715.3635 | 2021-22 £ÉÃ ¸Á°£À ¤ÃrgÀÄªÀ PÁAiÀÄðzÉÃ±ÀUÀ¼À MlÄÖ ªÉÆvÀÛ:- | 207715.3635 | 0
zÀÈrüÃPÀj¸ÀÄªÀÅzÉ£ÉAzÀgÉ F CAzÁdÄ¥ÀnÖAiÀÄ ªÉÆvÀÛªÀ£ÀÄß 2021-22 £ÉÃ ¸Á°£À°è ¤ÃqÀ¯ÁzÀ §eÉmï£À°è ¨sÀj¸À§ºÀÄzÁVzÉ ªÀÄvÀÄÛ ¤UÀªÀÄ¢AzÀ ¤UÀ¢ ¥Àr¹zÀ §eÉmï «ÄwAiÀÄ°è EgÀÄvÀÛzÉ.
¸ÀºÁAiÀÄPÀ PÁAiÀÄð¤ªÁðºÀPÀ EAf¤AiÀÄgï(PÀbÉÃj) |  | ¯ÉPÁÌ¢üPÁj
PÁAiÀÄð ªÀÄvÀÄÛ ¥Á®£Á «¨sÁUÀ |  | PÁAiÀÄð ªÀÄvÀÄÛ ¥Á®£Á «¨sÁUÀ
ZÁ.«.¸À.¤.¤ PÀÈµÀÚgÁd£ÀUÀgÀ |  | ZÁ.«.¸À.¤.¤ PÀÈµÀÚgÁd£ÀUÀgÀ
PÁAiÀÄð¤ªÁðºÀPÀ EAf¤AiÀÄgï
PÁAiÀÄð ªÀÄvÀÄÛ ¥Á®£Á «¨sÁUÀ
ZÁ.«.¸À.¤.¤ PÀÈµÀÚgÁd£ÀUÀgÀ

## LOAD BEFORE
CHAMUNDESWARI ELECTRICITY SUPPLY CORPORATION LIMITED
ESTIMATE FOR CREATING INFRASTRUCTURE TO REGULARISED IP SETS UNDER PARTIAL TURNKEY BASIS
SECTION OFFICER NAME :MAHADEV.D | [8 empty] | EST NO/DATE : TM-330 05/02/2022
SECTION : HOSUR | [8 empty] | VILLAGE NAME : BENAGANAHALLI
SUBDIVISION : K.R.NAGARA | [8 empty] | FEEDER NAME : KOTHAVALLI IP
EXISTING DTC CODE :1512CL | [8 empty] | EXISTING TRANSFORMER CAPACITY: 25KVA
NO OF IP SETS ON EXISTING TRANS:06 AUTH:06 UNAUTH:00 | [8 empty] | CONNECTED LOAD OF THE TRANSFORMER: 30HP
NO OF IPS/LOAD TRANSFERED TO PROPOSED 25 KVA TRANSFORMER: | [8 empty] | 03 /15HP
DWA No & Date.:CESC/GM(P)/DGM(P)/AGM(P-1)/2021-22/14111-13 Dated: 26.11.2021
EXISTING TRANSFORMER LOAD DETAILS
1 | IP enumeration of the above DTC completed on |  |  |  | and 06 No RR No were painted on the poles.
2 | Un-Authorised IP Sets Disconnected are : |  |  | 1 | Nos
3 | Date of Spot Inspection |  |  | 2022-11-18
4 | IP Sets details are as below
SL No | R R No | Pole No | Name | cescip.com/dishaank |  |  | UIP SET CODE @ cescip.com | Load in HP | Date of Service | Docket open on | Amount paid details
|  |  |  | Sy No | Lattitude | Longitude |  |  |  |  | D2/ISD | RT No | Penalty/ Devlopment Charges | RT No
1 | KRHIP55039 |  | SHANKAREGOWDA S/O LATE KALEGOWDA | 111 | 12.4645 | 76.2375 |  | 5 | 2015-03-31 |  | 4150 | 223010003573
2 | KRHIP60715 |  | B C NAGENDREGOWDACHANNEGOWDA | 109 | 12.4642 | 76.2374 |  | 5 | 2018-12-13 |  | 5500 | 25921
3 | KRIP1999 |  | B.S.NAGARAJEGOWDA | 104 | 12.4227 | 76.2353 |  | 5 | 2001-10-05 |  | 2700 | 10940
4 | KIPATL1771 |  | B.T.SWAMYGOWDA | 104 | 12.4626 | 76.235 |  | 5 | 2002-03-23 |  | 4500 | 6944
5 | KRIP2340 |  | B N SOMA SHANKAR | 104 | 12.463 | 76.2351 |  | 5 | 2005-04-30 |  | 3160 | 10383
6 | BGIP33 |  | THIMAEGOWDA | 100 | 12.4641 | 76.234 |  | 5 | 2000-12-30 |  | 1500 | 10661
9
10
11
12
13
14
15
16
17
18
19
20
21
21
22
23
24
30
| Seenior Assistant O&M Subdivision,CESC, K R Nagara |  |  | Junior Engineer(Ele), O&M Section, CESC, HOSUR | [5 empty] | Assistant Executive Engineer(Ele) O&M Sub-Division, CESC,KR Nagara

## LOAD AFTER
CHAMUNDESWARI ELECTRICITY SUPPLY CORPORATION LIMITED
ESTIMATE FOR CREATING INFRASTRUCTURE TO REGULARISED IP SETS UNDER PARTIAL TURNKEY BASIS
SECTION OFFICER NAME :MAHADEV.D | [8 empty] | EST NO/DATE : TM-330 05/02/2022
SECTION : HOSUR | [8 empty] | VILLAGE NAME : BENAGANAHALLI
SUBDIVISION : K.R.NAGARA | [8 empty] | FEEDER NAME : KOTHAVALLI IP
EXISTING DTC CODE :1512CL | [8 empty] | EXISTING TRANSFORMER CAPACITY: 25KVA
NO OF IPS/LOAD TRANSFERED TO PROPOSED 25 KVA TRANSFORMER: | [8 empty] | 03 /15HP
DWA No & Date.:CESC/GM(P)/DGM(P)/AGM(P-1)/2021-22/14111-13 Dated: 26.11.2021
PROPOSED TRANSFORMER LOAD DETAILS AFTER REGULARISATION
1 | IP enumeration of the above DTC completed on |  |  |  | RR Numbers of IP sets transfered to new DTC were painted on the poles.
SL No | R R No | Pole No | Name | As in CESC IP.Com/Dishaank |  |  | UIP SET CODE @ cescip.com | Load in HP | Date of Service | Docket open on | Amount paid details
|  |  |  | Sy No | Lattitude | Longitude |  |  |  |  | D2/ISD | RT No | Penalty/ Devlopment Charges | RT No
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21 | [7 empty] | 5
Senior Assistant, O&M Subdivsion, CESC,K R Nagara | [10 empty] | Assistant Executive Engineer(Ele) O&M Sub-Division, CESC,KR Nagara
Junior Engineer(Ele), O&M Section, CESC, HOSUR

## Sketch
CHAMUNDESWARI ELECTRICITY SUPPLY CORPORATION LIMITED
ESTIMATE FOR CREATING INFRASTRUCTURE TO REGISTERED/ REGULARISED IP SETS UNDER TOTAL TURNKEY BASIS
SECTION OFFICER NAME :MAHADEV.D | [5 empty] | EST NO/DATE : TM-330 05/02/2022
SECTION : HOSUR | [5 empty] | VILLAGE NAME : BENAGANAHALLI
SUBDIVISION : K.R.NAGARA | [5 empty] | FEEDER NAME : KOTHAVALLI IP
EXISTING DTC CODE :1512CL | [5 empty] | EXISTING TRANSFORMER CAPACITY: 25KVA
NO OF IP SETS ON EXISTING TRANS:06 AUTH:06 UNAUTH:00 | [5 empty] | CONNECTED LOAD OF THE TRANSFORMER: 30HP
NO OF IPS/LOAD TRANSFERED TO PROPOSED 25 KVA TRANSFORMER: | [5 empty] | 03 /15HP
LATTI
|  |  | LONGI |  | LATTI |  | LATTI
|  |  | SURVEY NO |  | LONGI | J | LONGI |  |  |  | LATTI
|  | LATTI | RR NO |  | SURVEY NO | 0.4KM | SURVEY NO |  |  |  | LONGI
|  | LONGI | E |  | RR NO | 10HP | RR NO | P |  |  | SURVEY NO
|  | SURVEY NO | [8 empty] | RR NO
RR NO
NAME |  | C
EXISTING 100KVA |  |  | 0.6KM | LATTI |  |  |  | 0.15KM |  | LATTI
DTC Code |  |  |  | LONGI | I |  | LATTI |  |  | LONGI
DTR Code |  |  |  | SURVEY NO | 0.2KM |  | LONGI | O |  | SURVEY NO | 0.4KM
|  | 0.2KM |  | RR NO |  |  | SURVEY NO | 0.1KM |  | RR NO
| 0.1KM |  | 0.13KM | F | 0.2KM | 0.3KM | RR NO |  |  | 0.15KM
| A | B 0.1KM | D |  |  | H |  | N | 0.25KM
0.3KM
|  |  |  | 0.3KM |  | L | 10HP |  |  | 0.2KM
LATTI
[6 empty] | 0.2 KM | LONGI
SURVEY NO
|  |  |  | G |  |  | RR NO |  |  | LATTI
EXISTING 63KVA |  |  |  | LATTI |  | M |  |  |  | LONGI
DTC Code |  |  |  | LONGI |  |  | LATTI |  |  | SURVEY NO
DTR Code |  |  |  | SURVEY NO |  |  | LONGI |  |  | RR NO
|  |  |  | RR NO |  | 0.05 KM | SURVEY NO
RR NO
PROPOSED 25 KVA
|  |  |  | DTC Code |  |  |  |  | EXISTING IP feeder(Name)
|  |  |  | DTR Code |  |  |  |  | Proposed 11 Kv Tapping Line
EXISTING LT Line
NOTE :SKETCH SHOULD INCLUDE ALL THIS DETAILS EVEN IF IT IS HAND DRAWN | [8 empty] | Proposed LT Extension
9 Mtr PSC Pole
9 Mtr RCC Pole
8 Mtr PSC Pole
8 Mtr RCC Pole
Existing Adagur IP Feeder KR Nagara MUSS
| Junior Engineer(Ele), O&M Section, CESC, HOSUR | [5 empty] | Assistant Executive Engineer(Ele) O&M Sub-Division, CESC,KR Nagara

## diV rEPORT (hidden)
CHAMUNDESWARI ELECTRICITY SUPPLY CORPORATION LIMITED
#REF! |  | #REF!
DWA.No & Date.: DWA.No. CESC/GM(P)/DGM(P)/AGM(P-1)/2018-19/DWA:171-172/6608-11 dated: 04.07.2018 for K.R Nagara & Saligrama Sub-Division
#REF!
#REF!
Abstract: | #REF!
Sechedule 1:Extention of HT line | 26541.24
Sechedule 2:Providing 1X25 KVA DTC | #REF!
Sechedule 3:Extension of LT line | #REF!
Total Estimate Cost | #REF!
This Proposal amounting to Rs 00 of awarding the above said work has been prepared as per the sanctioned work order No:…………………
Asst. Exe. Engineer (Tech), O&M Division, CESC, Krishnaraja Nagar | Asst. Exe. Engineer ( Off), O&M Division, CESC, Krishnaraja Nagar
Exe. Engineer ( Elec), O&M Division, CESC
Krishnaraja Nagar

## WA (hidden)
Chamundeshwari Electricity Supply Corporation Ltd.
(A Government of Karnataka undertaking)
Corporate Office, |  |  |  |  | Office of the Executive Engineer (Ele)
# 29, Vijayanagara, 2nd stage, Hinkal, |  |  |  |  | O & M Division, CESC,
Mysore-570009. |  |  |  |  | Krishnaraja Nagar.
Web : www.cescmysore.org |  |  |  |  | Phone: 08223-297997
CIN: U40109KA2004SGC035177 |  |  |  |  | E-Mail – eecesckrnagara@gmail.com
No. CESC/KRN/EE(Ele)/AEE(o)/AET/2018-19/
To,
M/s. Chamundeshwari Electrical,
12th cross, Srinagara,
S.S Mata Road, Tumakuru-571204
Dear Sir/Madam,
Sub:- Issuing of work award.
Ref :- 1. Work Order No |  |  | KD-2201 |  | Dated | 21.01.2022
2 | DWA No & Date.:CESC/GM(P)/DGM(P)/AGM(P-1)/2021-22/14117-19 Dated: 26.11.2021
*******
In continuation of DWA vide ref 1 & 2the following work is awarded on Total Turnkey basis, under unit rate contract subject to the following conditions
· The work should be carried out as per the sanctioned estimate [enclosed copy] and all released material shall be returned to Divisional stores, CESC, Krishnaraja nagara through concerned Section Officer.
· The work shall be completed in all respect within 30 days from the date of this letter. Otherwise the penalty will be imposed as per DWA clause
· The material should be purchased from the approved vendors of CESC and the materials should be as per the approved specification of CESC.
· Materials shall be supplied duely taking the Dispatch Insrtuctions and shall be stored in a neat and accountable manner for easy inspection & verification.
· Materials before utilization & work after execution shall be got inspected by the concerned TA & QC Engineer/CESC authorities. You are requested to produce TA & QC inspection Report/Test Certificate.
· The work should be carried out under the guidance of concerned Sub-Division Asst. Executive Engineer (Ele) and under the supervision of concerned Section Officer CESC.
· The Distribution Transformer 4 star rated shall be tested at transformer testing center, Preferably at office of EE(Ele), CESC, Hunsur /K.R.Nagara test report shall be produced.
· Approval from Electrical Inspectorate/Railway Crossing shall be obtained from your end before commissioning of completed works.
· The joint inventory of the materilas utilized shall be taken by Agency and CESC authority/field officer and joint inventory report shall be submitted after completion of the work.
· The work shall be handed over to the Asst. Executive Engineer (Ele), O&M Sub- Division, CESC,Saligrama in all respects, after completion & commissioning of work.
· The bills shall be certified with details of R.R No, Date of service, details of Transformer Make, Serial no, YOM and capacity of transformer and transformer test Certificate No & Seal No certified by concerned CESC authorities
· Providing Safety to Men & Material etc., shall be your firm’s responsibility.
· The bill shall be submitted with in 30 days from the date of commissioning along with the documents mentioned in DWA vide Clause no 9.
Sl.No | Section | Budget Head |  | Description of work | W.O.No | Estimate Cost in Rs. as per CESC SR |  | Award Cost in Rs. (As per DWA)
1 | Bherya | 14-3207 |  | Creating infrastructure for UAIP sets in favour of Sri Rangegowda &others at Sambravalli village | KD-2201 | HT | 27440.0212 | 26541.24
[6 empty] | DTC | 176126.282 | 185665
[6 empty] | LT | 3673.555 | 3869.4
[6 empty] | DEC | 475.5053 | 403.164
TOTAL | [6 empty] | 207715.3635 | 216478.804
Yours faithfully,
Executive Engineer (Ele),
O&M Division, CESC,
Krishnaraja Nagara
Copy to:
· Asst. Executive Engineer (Ele), O & M Sub Division CESC, Saligrama for information and to submit the Bill after completion of the work.
· Accounts Officer, O&M Division, CESC, Krishnaraja nagara.
· AET/MF.
Total Turnkey Work Award No/Date. :
KRN/UNIP/SLG/103/15.11.2018

## DTC Savings
CHAMUNDESHWARI ELECTRICITY SUPPLY CORPORATION LIMITED
ESTIMATE FOR CREATING INFRASTRUCTURE TO REGISTERED/ REGULARISED IP SETS UNDER TOTAL TURNKEY BASIS | [6 empty] | =
SECTION OFFICER NAME :MAHADEV.D | [6 empty] | EST NO/DATE : TM-330 05/02/2022
SECTION : HOSUR | [6 empty] | VILLAGE NAME : BENAGANAHALLI
SUBDIVISION : K R NAGAR | [6 empty] | FEEDER NAME : KOTHAVALLI IP
EXISTING DTC CODE :1512CL | [6 empty] | EXISTING TRANSFORMER CAPACITY: 25KVA
NO OF IP SETS ON EXISTING TRANS:06 AUTH:06 UNAUTH:00 | [6 empty] | CONNECTED LOAD OF THE TRANSFORMER: 30HP
DWA No & Date.:CESC/GM(P)/DGM(P)/AGM(P-1)/2021-22/14111-13 Dated: 26.11.2021
Energy Savings
I - Energy losses on existing 25 KVA before Providing additional 25KVA Transformer at (1512CL ) BENAGANAHALLI IP limit T.C
| 0.15 | x | 10 | x | 10 | 15
| 0.4 | x | 25 | x | 25 | 250
| 0.1 | x | 30 | x | 30 | 90
EHP2XCCX24X365
DF2
[7 empty] | 355 | 0.0056 | 8760
2.25
[6 empty] | 355 | 7739.9467 | Units/An
II - Energy losses on Existing 25 KVA after Providing additional 1X25KVA Transformer
| 0.4 | x | 15 | x | 15 | 90
EHP2XCCX24X365
DF2
[7 empty] | 90 | 0.0056 | 8760
2.25
[6 empty] | 90 | 1962.24 | Units/An
III - Energy losses on Proposed 25 KVA Transformer-1
| 0.15 | x | 10 | x | 10 | 15
| 0.1 | x | 15 | x | 15 | 22.5
EHP2XCCX24X365
|  | x | 0 | x | 0 | 0 | DF2
|  | x | 0 | x | 0 | 0 | 37.5 | 0.0056 | 8760
|  | x | 0 | x | 0 | 0 |  | 2.25
[6 empty] | 37.5 | 817.6 | Units/An
I-(II+III)
|  |  |  | Total Saving |  | 4960.1067

## LTVR
CHAMUNDESHWARI ELECTRICITY SUPPLY CORPORATION LIMITED
ESTIMATE FOR CREATING INFRASTRUCTURE TO REGISTERED/ REGULARISED IP SETS UNDER TOTAL TURNKEY BASIS | [5 empty] | 0
SECTION OFFICER NAME :MAHADEV.D | [5 empty] | EST NO/DATE : TM-330 05/02/2022
SECTION : HOSUR | [5 empty] | VILLAGE NAME : BENAGANAHALLI
SUBDIVISION : K R NAGAR | [5 empty] | FEEDER NAME : KOTHAVALLI IP
EXISTING DTC CODE :1512CL | [5 empty] | EXISTING TRANSFORMER CAPACITY: 25KVA
NO OF IP SETS ON EXISTING TRANS:06 AUTH:06 UNAUTH:00 | [5 empty] | CONNECTED LOAD OF THE TRANSFORMER: 30HP
LTVR Chart( circuit 1)
I - LTVR Calculation on existing 25KVA (1512CL) BENAGANAHALLI IP limit T.C
| 0.15 | x | 10 | x | 1.5
| 0.4 | x | 25 | x | 10
| 0.1 | x | 30 | x | 3
[5 empty] | 14.5 | 0.6 | 8.7
|  |  | LTVR = | 8.7
II - LTVR Calculation of Existing 25 KVA after bifurcation 1 no of 25KVA additional Transformer
| 0.4 | x | 15 | x | 6
[5 empty] | 6 | 0.6 | 3.6
|  |  | LTVR = | 3.6
III - LTVR Calculation of Proposed 25KVA Transformer-1
| 0.15 | x | 10 | x | 1.5
| 0.1 | x | 15 | x | 1.5
|  | x |  |  | 0
|  | x |  |  | 0
|  | x |  |  | 0
[5 empty] | 3 | 0.6 | 1.8
|  |  | LTVR = | 1.8